Minutes 1.PP Meeting

Date: 17.1.2018

Time: 10:00  – 17:00

Place: Mistelbach (Barokschlössl)

Participants:
NÖ RU3: Peter Santner, Klemens Rybaczek

PP2 NIG: Gisela Reichholf, Martina Liehl-Rainer

PP3 NÖABB: Erwin Szlezak

PP4 KS NS MAS JMK: Vit Hrdousek

PP5 DSO: Antonin Okenka, Daria Ricarova

PP6 PZ: Martina Petrova

PP7 JMK: Tomas Grulich

PP8 KS NS MAS JCK: Tomas Novak, Marta Krejcickova, Milada Vopalkova, Adela Tomsovicova

PP9 JCK: Kamil Zimmermann, Ivana Randakova

Programme:

- 10:00 – 12:00 administrative Tasks

  - Short Introduction of all Participants

  - Infos concerning ERDF Contract

  - Projectreporting (Timetable + EMS)

  - Inputs Projectfolder

- 12:00 – 12:30 Lunch

- 12:30 – 16:00 Activities, Next Steps

  - Projecttimetable with Activities and Responsibilities

  - Changerequest (Is everything still like applicated?)

  - Preparing Start-Conference

  - Coordinating follow up Dates (Next PP-Meetings,…)

- 16:00 – 17:30 Excursion Soilprotection Plants (Windrow Headges)

Minutes:

Peter Santner greets all Partners and thanks for the Participation and congratulates for getting the Project approved. Special Thanks to our CZ-Partners for “fighting” for this Project.

The Meetinglanguage is set to English (with translation possibilities)

Each Person gives a short Introduction and their tasks in the Project.

Klemens Rybaczek takes the Moderation and leads through the Meeting.

- Info about ERDF Contract:
The ERDF Contract will be sent next week to the Leadpartner. Then also EMS Logins have to be created and Reporting is possible.

- Projectreporting:
 Submit Reports in Time!

Financial report only if more than 10.000€ for Periode and Partner

FLC check takes up to 90 days

We recommend Meeting with responsible FLC in order to check relevant points!

Always have eligiblity rules in mind!

- EMS-Reporting:

  - Available after ERDF-Contract Signature (LP)

  - „Projectreporting-Person“ (from each PP)

  - Activity Report = Linked with application!

    - Choose all Outputs where you have contributed during the reportingperiode and describe it.

    - Validate them with attachments (List of Participants, Fotos, Minutes, Scans, eg…) – Upload directly to the relevant Output

  - Financial Report = Linked with Budget!

    - Filling via Invoice-List (All relevant expenses have to be filled in)

    - Validate them directly with attachments (Invoices, Procurement documents,…)

    - Important: All Invoices have to contain “Project: Klimagrün” + Projectnumber: ATCZ142

  - Detailed Informations can be found in the EMS-Handbook – please read it

- Projectfolder
A first draft of the planned Projectfolder was shown from PP2 NIG Martina Liehl-Rainer.
the Input was, to produce maybe one folder wich contains both languages (CZ, DE).

- Lunchbreak

- Projectoverview
After the Lunchbreak the Activity, Responsibility and Budget Table was discussed. Therefore the Excel Controlling List was gone threw point for point.
Maintopics like Translation, Seminars, Equipment, Planting, … were discussed detailed.
Translation of Projectreports will be done from CZ-Partners and discussed during first Report.
For all other points it was agreed that each Partner has a look in detail at home and submits till 31.1.2017 all relevant informations.

Red marked points in the Excel Document should be changed!

- 1. Changerequest
As LP RU3 needs a Budgetshifting and many other Partners have changes as well, the first Changerequest will be done in mid of february.
Therefor all Partners agreed to send the relevant informations till 31.1.2017.

- Startconference
The Startconference was discussed and many points were fixed.

9.5.2018 / Tulln (UFT) / 10:00 – 17:30

Main Targetgroup (Other Projects, Initatives in the Field)

Programmedraft:

9:00 – 10:00		Arrival + (optional Excursion UFT)

10:00 – 10:45	Welcomming (also with politicians)

If possible also Ploitician from CZ

10:45 – 11:30	Projectpresentation (from 3 Regions)

11:30 – 11:45	Coffeebreak

11:45 – 12:45	Thematic Impulspresentation(s)

Do you have possible Speakers?

12:45 – 13:45	Lunchbreak

13:45 – 14:15	Guided Posterpresentations (other projects)

Each Partner can name 1 possible organisations

14:15 – 15:30	Networking, Discussions

15:30 – 17:30	Excursion (Garten Tulln) – with Bikes

We need official programme for inviting Politicians, Partners and interested people. 
CZ-Expert could be Dr. Jan Pokormy (South bohemia – Trebon) cooperates with many universities. -> Tomas Novak will contact him (30 minutes presentation)
Input Vit Hrdousek: Plant a Climate Tree at Conference.
Max. 120 persons.
Simultanios Translation will be provided (CZ  DE)

- Next Meeting
19. June 2018
Place: Budweis
Time and Programmedraft will be provided from LP.
Location and Catering will be organized from PP6-PZ

- Exkursion:
The Partners are invited to visit the regional Soilprotection palnts (Windrow Hedges)

Minutes: Klemens Rybaczek (with assistance of Martina Liehl-Rainer)