# Q3 2025 Clinical Trial Progress Report

Protocol: TRIAL-2025-001

# Executive Summary

This report summarizes the progress of the Phase III clinical trial TRIAL-2025-001 evaluating the efficacy and safety of Compound XR-7 in patients with moderate-to-severe rheumatoid arthritis. The trial is sponsored by MedPharm Global Inc. and is being conducted across three sites in the United States. As of the end of Q3 2025, overall enrollment stands at 125 of 150 target patients (83% completion).

# Study Overview

Study Title: A Randomized, Double-Blind, Placebo-Controlled Phase III Trial of Compound XR-7 for the Treatment of Moderate-to-Severe Rheumatoid Arthritis

Sponsor: MedPharm Global Inc.

Phase: III

ClinicalTrials.gov Identifier: NCT05001234

# Patient Enrollment

The following table summarizes enrollment status across all participating sites:

| Site | Enrolled | Target | Status |
| --- | --- | --- | --- |
| Memorial Hospital | 45 | 50 | On Track |
| City Medical Center | 28 | 50 | Behind Schedule |
| University Research | 52 | 50 | Complete |

# Safety Data

The Data Safety Monitoring Board (DSMB) reviewed all adverse events reported during Q3 2025. The following adverse events were noted:

Mild headache reported in 12% of treatment group vs. 8% in placebo group (Smith et al., 2024 [1])

Gastrointestinal discomfort in 7% of treatment group vs. 5% in placebo group (Johnson & Lee, 2023 [2])

No serious adverse events (SAEs) were reported during this period (DSMB Report, August 2025 [3])

The overall safety profile of Compound XR-7 remains consistent with previous trial phases. No dose modifications or study protocol amendments were required.

# Conclusions

The trial continues to progress satisfactorily. Enrollment at Memorial Hospital and University Research is on or ahead of schedule. City Medical Center requires additional recruitment efforts to meet the target enrollment by the end of Q4 2025. The DSMB has recommended continuation of the trial without modifications.

# References

[1] Smith, A.B., et al. (2024). "Headache incidence in XR-7 Phase II trials." Journal of Clinical Pharmacology, 64(3), 221-230.

[2] Johnson, C.D., & Lee, M.K. (2023). "Gastrointestinal tolerability of novel anti-inflammatory compounds." Pharmacology Reviews, 18(2), 145-158.

# [3] Data Safety Monitoring Board. (2025). "TRIAL-2025-001 Interim Safety Report, August 2025." Internal Report, MedPharm Global Inc.